## Budget Request
Materials | Quantity | Price | Subtotal | Use | Link
Arduino Nicla Sense ME | 1 | 82.8 | 82.8 | State of the art sensors and powerful onboard CPU in one package | https://store-usa.arduino.cc/products/nicla-sense-me?selectedStore=us | .
Arduino Nano 33 BLE Sense Rev2 | 1 | 40.5 | 40.5 | Variety of sensors and AI enabled CPU with Bluetooth Onboard | https://store-usa.arduino.cc/products/nano-33-ble-sense-rev2 | .
Raspberry Pi 5 | 1 | 80 | 80 | Powerful SBC for mobile computing, collecting data and training on the data on the go | NA
Adafruit 9-DOF Absolute Orientation IMU | 1 | 34.95 | 34.95 | To be implemented with ESP32, accurate IMU | https://www.adafruit.com/product/2472 | .
ESP32 | 1 | 10 | 10 | Powerful microcontroller with WiFi and BLE | https://www.amazon.com/HiLetgo-ESP-WROOM-32-Development-Microcontroller-Integrated/dp/B0718T232Z | .
Hand Glove | 1 | 20 | 20 | For data collection system, used as a mount for hands | https://www.amazon.com/ihuan-Professional-Protection-Ventilation-Training/dp/B07D2Y91LS/ref=sr_1_6?keywords=Hand%2BGLove%2Bgym&qid=1697588733&sr=8-6&th=1 | .
Power Bank/Batteries | 1 | 30 | 30 | To power the mobile setup, components TBD
Misc (Attachments, 3D printing filament) | 1 | 50 | 50 | Others
Total |  |  | 348.25

## Chart Data
Create a Date Tracking Gantt Chart in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Machine Learning on Embedded Systems to Assess Correct Form During Weight Training
Milestones header for the milestone table is in cell B3. Tasks header for the tasks table is in cell G3. | Milestones |  |  |  | Tasks
Milestone table headers are in cells B5 through E5. Tasks table headers are in cells G5 through J5. Milestone sample data is in cells B6 through E11. Tasks sample data is in cells G6 through J17. The next instruction is in cell A21. | No. | Position | Date | Milestone | No. | Start Date | End Date | Task | Duration in days | Days
| 1 | 1 | 2024-01-30 | Data collection method devised | 1 | 2024-01-11 | 2024-04-30 | Documentation | 111 | 110
| 2 | 2 | 2024-01-30 | Data collection with SDFC staff scheduled | 2 | Fall 2023 | Fall 2023 | Analysis of the state-of-the-art |  | NA
| 3 | 3 | 2024-02-24 | Hardware Synthesized | 3 | Fall 2023 | 2024-01-10 | Study of relevant ML Algorithms |  | NA
| 4 | 4 | 2024-03-05 | Data Collected | 4 | 2024-01-10 | 2024-01-30 | Plan Hardware (For data collection, training, deploying) |  | 20
| 5 | 5 | 2024-03-25 | ML Models trained and compared | 5 | 2024-01-10 | 2024-01-30 | Plan Data Collection with SDFC Staff |  | 20
| 6 | 6 | 2024-04-25 | Research Paper Completed | 6 | 2024-01-30 | 2024-02-14 | Order materials and wait for delivery | 16 | 15
[5 empty] | 8 | 2024-02-14 | 2024-02-24 | Hardware Synthesis |  | 10
[5 empty] | 7 | 2024-02-24 | 2024-03-05 | Data Collection |  | 10
[5 empty] | 9 | 2024-02-29 | 2024-03-25 | Training models and experimenting with them |  | 25
[5 empty] | 10 | 2024-03-25 | 2024-04-04 | Buffer |  | 10
[5 empty] | 11 | 2024-04-05 | 2024-04-10 | Finalizing poster for FURI |  | 5
[5 empty] | 12 | 2024-04-05 | 2024-04-25 | Summarizing results into a research paper |  | 20
Formulas:
End Date = Tasks[[#This Row],[Start Date]]+[Days]
End Date = Tasks[[#This Row],[Start Date]]+Tasks[[#This Row],[Days]]
Start Date = [End Date, row above]
Start Date = [Start Date, row above]

## Gantt Chart
Gantt Chart
Task Milestone | 2024-01-11 | 2024-01-16 | 2024-01-21 | 2024-01-26 | 2024-01-31 | 2024-02-05 | 2024-02-10 | 2024-02-15 | 2024-02-20 | 2024-02-25 | 2024-03-01 | 2024-03-06 | 2024-03-11 | 2024-03-16 | 2024-03-21 | 2024-03-26 | 2024-03-31 | 2024-04-05 | 2024-04-10 | 2024-04-15 | 2024-04-20 | 2024-04-25 | 2024-04-30
Documentation
Analysis of the state-of-the-art (Fall 2023)
Study of relevant ML Algorithms (Fall 2023)
Plan Hardware (For data collection, training, deploying) | bar: 2024-01-11 to 2024-01-26
Plan Data Collection with SDFC Staff | bar: 2024-01-11 to 2024-01-26
Data collection method devised | bar: 2024-01-26
Data collection with SDFC staff scheduled | bar: 2024-01-26
Order materials and wait for delivery | bar: 2024-01-31 to 2024-02-15
Hardware Synthesis | bar: 2024-02-15 to 2024-02-20
Hardware Synthesized | bar: 2024-02-20
Data Collection | bar: 2024-02-25 to 2024-03-01
Data Collected | bar: 2024-03-01
Training models and experimenting with them | bar: 2024-03-01 to 2024-03-26
ML Models Trained and Compared | bar: 2024-03-26
Buffer | 2024-03-26: Buffer
Finalizing poster for FURI | bar: 2024-04-05 to 2024-04-10
Summarizing results into a research paper | bar: 2024-04-05 to 2024-04-20
Research Paper Completed | bar: 2024-04-20

## Dynamic Chart Data Hidden (hidden)
Title of this worksheet is in cell B1. | Dynamic Chart data, Do NOT edit or delete this worksheet!
Table title is in cells B2 and C2. |  | highlight
Table heading is in cells B3 and C3. These coordinates create the Today highlight in the chart. The first column marks the day, the second indicates to draw the line that highlights today. The first column date may change so the chart date range stays readable as the dates progress, however, a y co-ord of 0 indicates no line is drawn. Do not modify or delete this content or the charting may break. To no longer highlight Today's date, simply select "no" in the Chart Data worksheet in cell D2. The next instruction is in cell A7. | today highlight x co-ord | y co-ord
| 2024-01-10 | 0
| 2024-01-10 | 0
Table heading is in cell B7. The scrolling increment in cell B8 represents the data graphed and visually appearing in the Gantt Chart at any one time. Scrolling with the scroll bar at the top of the chart in row 1 of the Gantt Chart worksheet, will increment this number. The charting works best with single increments. The next instructin is in cell A10. | scroll increment
0
Table heading is in cell B10 and D10. The Charting Range helps select the appropriate range of tasks and milestones. Do not modify these fields. The ageoff number, keeps the chart readable by aging tasks from the range and only plotting those that are within the range. Do not modify this number. The next instruction is in cell A14. | Charting range |  | ageoff
| 2024-01-10 |  | 45
2024-01-25
Table heading for Dynamic Milestone Data is in cells B14 through E14. A note is in cell F14. This table creates the Gantt Chart in the Gantt Chart worksheet, plotting 7 milestones at a time. The data in this chart is auto generated based on the content in the table above. Do not edit or delete this table or its contents. The next instruction is in cell A17. | Tasks | Start date | Task duration in days | position | <-- this table creates the gantt chart, plotting 7 milestones at a time
| Documentation | 2024-01-11 | 15 | 8
| Analysis of the state-of-the-art | Fall 2023 |  | 7 |  | Milestone charting
Cells G15 trhrough I15 contain table headings for Dynamic Milestone Data. Data in this table may appear blank, dates may appear to be incorrect, do not fill in, edit, delete or otherwise modify this data or you risk overwriting formulas and breaking the chart graphing capability. The table allows for 15 milestones to be charted. To chart more than 15, simply expand the table to accommodate your number. Remember, only add the milestones in the Chart Data worksheet. Do not add any content to this table. A note is in cell J15. The next insruction is in cell A32. | Study of relevant ML Algorithms | Fall 2023 |  | 6 |  | Milestones | Date | Baseline | <-- this table creates the milestone markers in the gantt chart, plotting only those milestones that fit in the range of dates shown; up to 15 milestones
| Plan Hardware (For data collection, training, deploying) | 2024-01-10 | 16 | 5 |  |  | 2024-01-25
|  | 2024-01-10 | 0 |  |  |  | 2024-01-25
| Order materials and wait for delivery | 2024-01-30 | 16 | 3 |  |  | 2024-01-25
| Data Collection | 2024-02-24 | 0 | 2 |  |  | 2024-01-25
2024-01-25
2024-01-25
2024-01-25
2024-01-25
2024-01-25
2024-01-25
2024-01-25
2024-01-25
2024-01-25
2024-01-25
A note is in cell J32. This is the last instruction in this worksheet. | [6 empty] | 2024-01-25 |  | <--To chart more than 15 milestones, simply expand this table and enter new entries in the Milestone table in the Chart Data worksheet.